## 01_MASTER_GANTT
BIỂU ĐỒ GANTT THEO DÕI TIẾN ĐỘ DỰ ÁN VSIGN | [12 empty] | TIMELINE: 09/2026 – 02/2028 (PROPOSED)
VSign – Nghiên cứu và phát triển hệ thống nhận diện Ngôn ngữ ký hiệu Việt Nam theo thời gian thực, hiệu quả dữ liệu và có khả năng tổng quát hóa người ký sử dụng học chuyển giao, phục vụ giao tiếp đa ngôn ngữ
TIÊU ĐỀ DỰ ÁN |  | VSign – Nghiên cứu và phát triển hệ thống nhận diện Ngôn ngữ ký hiệu Việt Nam theo thời gian thực, hiệu quả dữ liệu và có khả năng tổng quát hóa người ký sử dụng học chuyển giao, phục vụ giao tiếp đa ngôn ngữ | [5 empty] | TÊN TRƯỜNG |  | Đại học Phenikaa
TÊN DỰ ÁN |  | VSign | [5 empty] | NGƯỜI QUẢN LÝ DỰ ÁN |  | Đặng Đại Đạt
TÊN TIẾNG ANH |  | VSign: A Data-Efficient and Signer-Generalizable Real-Time Vietnamese Sign Language Recognition System Using Transfer Learning for Multilingual Communication | [5 empty] | NGÀY CẬP NHẬT |  | 2026-09-21
WBS / TASK DATA | [11 empty] | Status I: auto formula; có thể ghi đè thủ công khi cần | 09/2026 |  |  |  |  | 10/2026 |  |  |  | 11/2026 |  |  |  | 12/2026 |  |  |  |  | 01/2027 |  |  |  | 02/2027 |  |  |  | 03/2027 |  |  |  |  | 04/2027 |  |  |  | 05/2027 |  |  |  | 06/2027 |  |  |  |  | 07/2027 |  |  |  | 08/2027 |  |  |  |  | 09/2027 |  |  |  | 10/2027 |  |  |  | 11/2027 |  |  |  |  | 12/2027 |  |  |  | 01/2028 |  |  |  | 02/2028
WBS | Tiêu đề công việc | Workstream | Người phụ trách | Ngày bắt đầu | Ngày kết thúc | Thời gian (ngày) | % hoàn thành | Trạng thái | Priority | Dependency | Deliverable | Ghi chú | time axis 2026-09-01 to 2028-02-29
1 | Project Definition & Research Direction | Phase | Cả nhóm | 2026-09-01 | 2026-09-30 | 30 | 66.67% | In Progress |  |  |  | Proposed phase baseline
1.1 | Khóa tên đề tài chính thức và research positioning | Project Management | Project Lead | 2026-09-01 | 2026-09-10 | 10 | 100% | Completed | P0 – Critical |  | Project title + research positioning | Đã chốt theo baseline 21/09/2026
1.2 | Xác nhận research story: low-resource VSL → transfer learning → data efficiency → signer generalization → robust real-time recognition | Research | Research | 2026-09-05 | 2026-09-14 | 10 | 100% | Completed | P0 – Critical | 1.1 | Research direction statement | Đã chốt
1.3 | Hoàn thiện VSign Project Overview v0.1 theo hướng đã chốt | Documentation | Documentation | 2026-09-09 | 2026-09-18 | 10 | 100% | Completed | P0 – Critical | 1.2 | VSign Project Overview v0.1 | Đã hoàn thiện trong project
1.4 | Xây Master Gantt/WBS và hệ thống theo dõi tiến độ | Project Management | Project Lead | 2026-09-13 | 2026-09-22 | 10 | 100% | Completed | P1 – High | 1.3 | VSign Project Master Gantt | Proposed baseline; file hiện tại
1.5 | Thiết lập Decision Log / Risk Register / Issue Log | Project Management | Project Lead | 2026-09-17 | 2026-09-26 | 10 | 0% | In Progress | P1 – High | 1.4 | Governance templates | Proposed
1.6 | Chốt kiến trúc tài liệu và quy tắc change control | Documentation | Documentation | 2026-09-21 | 2026-09-30 | 10 | 0% | In Progress | P1 – High | 1.3 | Documentation governance note | Proposed
M01 | Project direction baseline locked | Milestone | Project Lead | 2026-09-30 | 2026-09-30 | 1 | 100% | Completed | P0 – Critical | 1.4 | Tên đề tài, research story, Project Overview và Master Gantt baseline được chốt | Milestone
2 | Literature Review | Phase | Cả nhóm | 2026-09-07 | 2026-10-18 | 42 | 0% | In Progress |  |  |  | Proposed phase baseline
2.1 | Thu thập literature VSL/SLR giai đoạn nền tảng và gần đây | Research | Research | 2026-09-07 | 2026-09-24 | 18 | 0% | In Progress | P0 – Critical | 1.2 | Core paper library | Ưu tiên VSL + CSLR + transfer learning
2.2 | Đọc và tóm tắt VSL Review 2026, VSL400 2026, CrossViViT 2025, Camgoz 2020 và các công trình liên quan | Research | Research | 2026-09-11 | 2026-09-28 | 18 | 0% | In Progress | P0 – Critical | 2.1 | Paper summaries | Current evidence base
2.3 | Lập Literature Matrix: dataset, signers, input, model, split, metric, limitation | Research | Research | 2026-09-16 | 2026-10-03 | 18 | 0% | In Progress | P1 – High | 2.2 | Literature Matrix | Proposed
2.4 | Tổng hợp hướng community / real-world / accessibility để nhận diện khoảng cách lab–deployment | Research | Research | 2026-09-21 | 2026-10-08 | 18 | 0% | In Progress | P2 – Medium | 2.2 | Community & deployment notes | Nguồn ngoài literature chỉ dùng bổ trợ
2.5 | Phân tích research gap và novelty phù hợp VSign | Research | Research | 2026-09-26 | 2026-10-13 | 18 | 0% | Not Started | P0 – Critical | 2.3 | VSign Research Gap Analysis | Không khóa novelty nếu evidence chưa đủ
2.6 | Viết Literature Review bản 1 | Documentation | Documentation | 2026-10-01 | 2026-10-18 | 18 | 0% | Not Started | P1 – High | 2.5 | Literature Review draft | Proposed
M02 | Literature review & research gap completed | Milestone | Research | 2026-10-31 | 2026-10-31 | 1 | 0% | Not Started | P0 – Critical | 2.6 | Literature Matrix + Research Gap Analysis đủ để khóa proposal | Milestone
3 | Research Design | Phase | Cả nhóm | 2026-10-01 | 2026-11-04 | 35 | 0% | Not Started |  |  |  | Proposed phase baseline
3.1 | Khóa Research Questions RQ1–RQ6 ở mức proposal | Research | Research | 2026-10-01 | 2026-10-15 | 15 | 0% | Not Started | P0 – Critical | 2.5 | Research Questions set | Bám baseline hiện tại
3.2 | Xác định hypotheses / expected comparisons không gắn KPI tùy ý | Research | Research | 2026-10-05 | 2026-10-19 | 15 | 0% | Not Started | P1 – High | 3.1 | Hypothesis table | Proposed
3.3 | Chốt Experiment Matrix E1–E8; E9 optional | Research | Research | 2026-10-09 | 2026-10-23 | 15 | 0% | Not Started | P0 – Critical | 3.1 | Experiment Matrix | Bám current direction
3.4 | Thiết kế Evaluation Protocol: Accuracy, Macro-F1, GER, latency, resource, reliability | Research | Research | 2026-10-13 | 2026-10-27 | 15 | 0% | Not Started | P0 – Critical | 3.3 | Evaluation Protocol draft | Không dùng accuracy duy nhất
3.5 | Thiết kế reproducibility protocol: seeds, configs, model/data version, experiment tracking | AI | AI | 2026-10-17 | 2026-10-31 | 15 | 0% | Not Started | P1 – High | 3.4 | Reproducibility checklist | Proposed
3.6 | Hoàn thiện Research Proposal | Documentation | Documentation | 2026-10-21 | 2026-11-04 | 15 | 0% | Not Started | P0 – Critical | 3.1,3.3,3.4 | VSign Research Proposal | Proposed
M03 | Research design / proposal approved | Milestone | Research | 2026-11-15 | 2026-11-15 | 1 | 0% | Not Started | P0 – Critical | 3.6 | RQ1–RQ6, E1–E8, evaluation protocol và proposal được duyệt | Milestone
4 | VSL Dataset Planning | Phase | Cả nhóm | 2026-10-15 | 2026-11-21 | 38 | 0% | Not Started |  |  |  | Proposed phase baseline
4.1 | Xác minh điều kiện truy cập / Data Usage Agreement của VSL400 | Dataset | Dataset | 2026-10-15 | 2026-10-28 | 14 | 0% | Not Started | P0 – Critical | 2.2 | VSL400 access decision | VSL400 là controlled access; không giả định đã có quyền
4.2 | Chốt tiêu chí vocabulary MVP 30–50 gloss | Dataset | Dataset | 2026-10-19 | 2026-11-01 | 14 | 0% | Not Started | P0 – Critical | 3.1 | MVP vocabulary criteria | 30–50 là scope đã chốt ở mức Overview
4.3 | Xây danh sách vocabulary MVP dự kiến | Dataset | Dataset | 2026-10-23 | 2026-11-05 | 14 | 0% | Not Started | P1 – High | 4.2 | MVP vocabulary v0 | Cần VSL expert review nếu khả thi
4.4 | Xác định benchmark subset 100–400 classes nếu dữ liệu/tài nguyên cho phép | Research | Research | 2026-10-27 | 2026-11-09 | 14 | 0% | Not Started | P2 – Medium | 4.1 | Benchmark subset plan | Không bắt buộc MVP
4.5 | Thiết kế metadata schema: signer/session/handedness/view/lighting/speed/quality | Dataset | Dataset | 2026-10-31 | 2026-11-13 | 14 | 0% | Not Started | P0 – Critical | 4.2 | Dataset schema | Bám robustness & generalization RQ
4.6 | Thiết kế signer-independent split và leakage-check protocol | Dataset | Dataset | 2026-11-04 | 2026-11-17 | 14 | 0% | Not Started | P0 – Critical | 4.5 | Split protocol | Bắt buộc cho claim generalization
4.7 | Soạn self-collection / consent / storage protocol | Dataset | Dataset | 2026-11-08 | 2026-11-21 | 14 | 0% | Not Started | P0 – Critical | 4.5 | Collection & consent protocol | TBD policy phải được phê duyệt trước collection chính thức
M04 | Dataset protocol completed | Milestone | Dataset | 2026-11-30 | 2026-11-30 | 1 | 0% | Not Started | P0 – Critical | 4.7 | Vocabulary, source/access, metadata, signer split, consent/collection protocol sẵn sàng | Milestone
5 | Data Collection | Phase | Cả nhóm | 2026-11-15 | 2027-02-04 | 82 | 0% | Not Started |  |  |  | Proposed phase baseline
5.1 | Nhập metadata và tài nguyên VSL400 được cấp quyền (nếu truy cập được) | Dataset | Dataset | 2026-11-15 | 2026-12-20 | 36 | 0% | Not Started | P0 – Critical | 4.1 | Imported external dataset inventory | Phụ thuộc access
5.2 | Tuyển người ký và hoàn tất consent nếu cần tự thu | Dataset | Dataset | 2026-11-24 | 2026-12-29 | 36 | 0% | Not Started | P0 – Critical | 4.7 | Signer roster + consent records | Ưu tiên diversity
5.3 | Chạy pilot recording để kiểm tra protocol | Dataset | Dataset | 2026-12-03 | 2027-01-07 | 36 | 0% | Not Started | P1 – High | 5.2 | Pilot recording report | Proposed
5.4 | Thu dữ liệu vòng 1 cho vocabulary MVP | Dataset | Dataset | 2026-12-13 | 2027-01-17 | 36 | 0% | Not Started | P0 – Critical | 5.3 | Self-collected raw data v0 | Ưu tiên nhiều signer hơn nhiều repetition từ ít signer
5.5 | Thu mẫu robustness có kiểm soát: view/lighting/speed/handedness/occlusion | Dataset | Dataset | 2026-12-22 | 2027-01-26 | 36 | 0% | Not Started | P1 – High | 5.4 | Robustness subset | Phục vụ RQ4/E6
5.6 | Kiểm kê completeness, backup và access permissions | Dataset | Dataset | 2026-12-31 | 2027-02-04 | 36 | 0% | Not Started | P1 – High | 5.4,5.5 | Collection QC report | Proposed
6 | Data Processing & Annotation | Phase | Cả nhóm | 2026-12-01 | 2027-03-02 | 92 | 0% | Not Started |  |  |  | Proposed phase baseline
6.1 | Thiết lập cấu trúc thư mục, dataset manifest và versioning | Dataset | Dataset | 2026-12-01 | 2027-01-05 | 36 | 0% | Not Started | P0 – Critical | 5.1,5.4 | Dataset pipeline v0 | Proposed
6.2 | Chuẩn hóa video/frame sampling và quality checks | Dataset | Dataset | 2026-12-10 | 2027-01-14 | 36 | 0% | Not Started | P1 – High | 6.1 | Preprocessed video set | Candidate preprocessing; chưa khóa tool
6.3 | Trích xuất hand/pose/selected-face landmarks | AI | AI | 2026-12-19 | 2027-01-23 | 36 | 0% | Not Started | P0 – Critical | 6.2 | Landmark feature set | MediaPipe là candidate
6.4 | Rà soát / gán nhãn gloss và metadata | Dataset | Dataset | 2026-12-29 | 2027-02-02 | 36 | 0% | Not Started | P0 – Critical | 6.2 | Verified labels | Cần review domain khi khả thi
6.5 | Deduplicate và kiểm tra signer/session leakage | Dataset | Dataset | 2027-01-07 | 2027-02-11 | 36 | 0% | Not Started | P0 – Critical | 6.4 | Leakage audit | Bắt buộc trước final split
6.6 | Tạo train/validation/test split theo signer | Dataset | Dataset | 2027-01-16 | 2027-02-20 | 36 | 0% | Not Started | P0 – Critical | 6.5 | Signer-independent split v1 | Core evaluation asset
6.7 | Tạo Dataset Card v1 và statistics report | Documentation | Documentation | 2027-01-26 | 2027-03-02 | 36 | 0% | Not Started | P1 – High | 6.6 | Dataset Card v1 | Proposed
M05 | Dataset v1 + signer split ready | Milestone | Dataset | 2027-03-31 | 2027-03-31 | 1 | 0% | Not Started | P0 – Critical | 6.7 | Dataset v1, QC, leakage audit, signer-independent split và Dataset Card v1 hoàn thành | Milestone
7 | Baseline AI Model | Phase | Cả nhóm | 2027-01-01 | 2027-02-26 | 57 | 0% | Not Started |  |  |  | Proposed phase baseline
7.1 | Xây Model A: hand landmarks + LSTM baseline | AI | AI | 2027-01-01 | 2027-01-25 | 25 | 0% | Not Started | P0 – Critical | 6.3,6.6 | Model A v1 | Engineering baseline
7.2 | So sánh LSTM với GRU/TCN lightweight baseline | AI | AI | 2027-01-07 | 2027-01-31 | 25 | 0% | Not Started | P1 – High | 7.1 | E1 baseline comparison | Phục vụ E1
7.3 | Xây Model B: hand + pose temporal baseline | AI | AI | 2027-01-14 | 2027-02-07 | 25 | 0% | Not Started | P0 – Critical | 6.3,6.6 | Model B HP v1 | Phục vụ RQ3
7.4 | Mở rộng Model B: hand + pose + selected face | AI | AI | 2027-01-20 | 2027-02-13 | 25 | 0% | Not Started | P1 – High | 7.3 | Model B HPF v1 | Selected face, không mặc định toàn bộ face landmarks
7.5 | Đánh giá baseline: Accuracy/Macro-F1/confusion matrix | Research | Research | 2027-01-27 | 2027-02-20 | 25 | 0% | Not Started | P0 – Critical | 7.1,7.3,7.4 | Baseline evaluation report | Proposed
7.6 | Profile inference baseline: FPS, p50/p95 latency, RAM/VRAM | AI | AI | 2027-02-02 | 2027-02-26 | 25 | 0% | Not Started | P1 – High | 7.5 | Baseline performance profile | Real-time evidence
8 | Signer-independent Recognition | Phase | Cả nhóm | 2027-03-01 | 2027-04-27 | 58 | 0% | Not Started |  |  |  | Proposed phase baseline
8.1 | Xây signer-independent dataloader/evaluation pipeline cố định | AI | AI | 2027-03-01 | 2027-03-25 | 25 | 0% | Not Started | P0 – Critical | 6.6 | Signer-independent evaluation pipeline | Không dùng random split cho claim generalization
8.2 | Chạy seen-signer benchmark cho Model A/B | AI | AI | 2027-03-07 | 2027-03-31 | 25 | 0% | Not Started | P2 – Medium | 8.1,7.5 | Seen-signer reference results | Chỉ để đối chiếu
8.3 | Chạy unseen-signer benchmark cho Model A | AI | AI | 2027-03-14 | 2027-04-07 | 25 | 0% | Not Started | P0 – Critical | 8.1,7.1 | Model A unseen-signer results | Core metric
8.4 | Chạy unseen-signer benchmark cho Model B | AI | AI | 2027-03-21 | 2027-04-14 | 25 | 0% | Not Started | P0 – Critical | 8.1,7.3,7.4 | Model B unseen-signer results | Core metric
8.5 | Phân tích per-signer và gesture-pair failures | Research | Research | 2027-03-27 | 2027-04-20 | 25 | 0% | Not Started | P1 – High | 8.3,8.4 | Generalization error analysis | Proposed
8.6 | So sánh random split vs signer-independent chỉ để minh họa leakage | Research | Research | 2027-04-03 | 2027-04-27 | 25 | 0% | Not Started | P2 – Medium | 8.1 | Leakage illustration | Không dùng random split làm kết luận chính
M06 | Model A/B baselines completed | Milestone | AI | 2027-05-15 | 2027-05-15 | 1 | 0% | Not Started | P0 – Critical | 8.5 | Baseline metrics và unseen-signer evaluation cho landmark models hoàn thành | Milestone
9 | Model Improvement & Experimentation | Phase | Cả nhóm | 2027-04-01 | 2027-07-03 | 94 | 0% | Not Started |  |  |  | Proposed phase baseline
9.1 | Chọn pretrained RGB/video backbone candidate | AI | AI | 2027-04-01 | 2027-05-06 | 36 | 0% | Not Started | P0 – Critical | 2.2,7.5 | Model C architecture decision | CrossViViT/video Transformer là evidence, không mặc định best
9.2 | Triển khai Model C cùng architecture với random initialization | AI | AI | 2027-04-09 | 2027-05-14 | 36 | 0% | Not Started | P0 – Critical | 9.1,6.6 | Model C Scratch | Control arm cho E3
9.3 | Triển khai Model C với pretrained initialization + fine-tuning | AI | AI | 2027-04-17 | 2027-05-22 | 36 | 0% | Not Started | P0 – Critical | 9.1,6.6 | Model C Pretrained | Treatment arm cho E3
9.4 | Chạy E3: Scratch vs Pretrained trên cùng input/split/protocol | Research | Research | 2027-04-26 | 2027-05-31 | 36 | 0% | Not Started | P0 – Critical | 9.2,9.3 | E3 Transfer Learning report | Core contribution
9.5 | Chạy E4: 10/25/50/75/100% labeled training data | Research | Research | 2027-05-04 | 2027-06-08 | 36 | 0% | Not Started | P0 – Critical | 9.2,9.3 | Data-efficiency learning curves | Core contribution
9.6 | Tổng hợp E2 representation ablation Hand vs HP vs HPF | Research | Research | 2027-05-13 | 2027-06-17 | 36 | 0% | Not Started | P1 – High | 7.5,8.4 | E2 representation report | RQ3
9.7 | Chạy E5/E6: unseen signer + robustness conditions | Research | Research | 2027-05-21 | 2027-06-25 | 36 | 0% | Not Started | P0 – Critical | 8.3,8.4,5.5,9.3 | Generalization & robustness report | RQ4
9.8 | Chọn research model và runtime candidate dựa trên accuracy–latency–resource | AI | AI | 2027-05-29 | 2027-07-03 | 36 | 0% | Not Started | P0 – Critical | 9.4,9.5,9.7 | Model selection decision | Có thể khác nhau giữa research và runtime
M07 | Core TL/data-efficiency/generalization experiments completed | Milestone | AI | 2027-07-31 | 2027-07-31 | 1 | 0% | Not Started | P0 – Critical | 9.8 | E2–E6 hoàn thành; research/runtime candidate được chọn | Milestone
10 | Continuous / Short-sequence Sign Recognition | Phase | Cả nhóm | 2027-08-01 | 2027-09-26 | 57 | 0% | Not Started |  |  |  | Proposed phase baseline
10.1 | Thiết kế short-sequence vocabulary / templates 2–5 gloss | Research | Research | 2027-08-01 | 2027-08-22 | 22 | 0% | Not Started | P1 – High | 4.3,9.8 | Short-sequence scope | Target sau core recognition
10.2 | Chuẩn bị / thu short-sequence samples | Dataset | Dataset | 2027-08-06 | 2027-08-27 | 22 | 0% | Not Started | P1 – High | 10.1,5.4 | Short-sequence dataset v0 | Proposed
10.3 | Triển khai streaming sliding window + no-sign/blank state | AI | AI | 2027-08-12 | 2027-09-02 | 22 | 0% | Not Started | P0 – Critical | 10.2,9.8 | Streaming decoder v1 | Target
10.4 | Triển khai duplicate suppression và temporal stability | AI | AI | 2027-08-18 | 2027-09-08 | 22 | 0% | Not Started | P0 – Critical | 10.3 | Temporal stabilization v1 | Phục vụ E7
10.5 | Đánh giá short-sequence bằng Gloss Error Rate | Research | Research | 2027-08-24 | 2027-09-14 | 22 | 0% | Not Started | P1 – High | 10.3,10.4 | Short-sequence evaluation | Target
10.6 | Decision gate: có đủ dữ liệu để thử full CSLR/CTC hay không | AI | Project Lead | 2027-08-30 | 2027-09-20 | 22 | 0% | Not Started | P0 – Critical | 10.5 | CSLR go/no-go decision | Không để full continuous chặn MVP
10.7 | Prototype CTC / continuous nếu gate = GO | AI | AI | 2027-09-05 | 2027-09-26 | 22 | 0% | Not Started | P3 – Low | 10.6 | Optional CSLR prototype | Stretch only
11 | Gloss-to-Vietnamese NLP | Phase | Cả nhóm | 2027-07-01 | 2027-08-29 | 60 | 0% | Not Started |  |  |  | Proposed phase baseline
11.1 | Chuẩn hóa gloss inventory và mapping rules | NLP | NLP | 2027-07-01 | 2027-07-26 | 26 | 0% | Not Started | P0 – Critical | 4.3,6.4 | Gloss language map | Proposed
11.2 | Xây rule/template gloss → Vietnamese baseline | NLP | NLP | 2027-07-07 | 2027-08-01 | 26 | 0% | Not Started | P0 – Critical | 11.1 | Language baseline v1 | Core language layer
11.3 | Thử constrained generation candidate nếu cần | NLP | NLP | 2027-07-14 | 2027-08-08 | 26 | 0% | Not Started | P2 – Medium | 11.2 | Constrained generator prototype | Không để LLM che lỗi recognition
11.4 | Xây semantic preservation / adequacy evaluation set | Research | Research | 2027-07-21 | 2027-08-15 | 26 | 0% | Not Started | P1 – High | 11.1 | Language evaluation set | Proposed
11.5 | Chạy E8: ground-truth gloss vs predicted gloss → Vietnamese | Research | Research | 2027-07-28 | 2027-08-22 | 26 | 0% | Not Started | P0 – Critical | 11.2,11.4,9.7 | Error-propagation report v1 | RQ6
11.6 | Chọn language layer cho MVP | NLP | NLP | 2027-08-04 | 2027-08-29 | 26 | 0% | Not Started | P0 – Critical | 11.2,11.3,11.5 | Language layer decision | Evidence-based
M08 | Short-sequence + language target reached | Milestone | AI / NLP | 2027-10-15 | 2027-10-15 | 1 | 0% | Not Started | P0 – Critical | 10.5,11.6 | 2–5 gloss target và gloss→Vietnamese layer có evaluation/limitations rõ | Milestone
12 | Multilingual Translation | Phase | Cả nhóm | 2027-09-01 | 2027-09-26 | 26 | 0% | Not Started |  |  |  | Proposed phase baseline
12.1 | Chốt target language MVP đầu tiên | NLP | Project Lead | 2027-09-01 | 2027-09-10 | 10 | 0% | Not Started | P1 – High | 11.6 | Target language decision | English là Proposed, chưa mặc định nếu team chọn khác
12.2 | Chọn translation provider/model candidate | NLP | NLP | 2027-09-05 | 2027-09-14 | 10 | 0% | Not Started | P1 – High | 12.1 | Translation decision record | Không tự train từ đầu
12.3 | Xây translation interface Vietnamese → target | NLP | NLP | 2027-09-09 | 2027-09-18 | 10 | 0% | Not Started | P0 – Critical | 12.2 | Translation adapter | Modular service
12.4 | Đánh giá câu ngắn: adequacy/obvious failures/latency | Research | Research | 2027-09-13 | 2027-09-22 | 10 | 0% | Not Started | P1 – High | 12.3 | Translation evaluation notes | Integration-level evaluation
12.5 | Thêm fallback / timeout / cache policy khi phù hợp | Backend | Backend | 2027-09-17 | 2027-09-26 | 10 | 0% | Not Started | P2 – Medium | 12.3 | Translation reliability logic | Proposed
13 | Text-to-Speech | Phase | Cả nhóm | 2027-09-15 | 2027-10-10 | 26 | 0% | Not Started |  |  |  | Proposed phase baseline
13.1 | Chọn TTS provider/model/voice candidate | NLP | NLP | 2027-09-15 | 2027-09-24 | 10 | 0% | Not Started | P1 – High | 12.1 | TTS decision record | TBD provider
13.2 | Xây TTS interface target text → audio | Backend | Backend | 2027-09-19 | 2027-09-28 | 10 | 0% | Not Started | P0 – Critical | 13.1 | TTS adapter | Integration layer
13.3 | Xử lý language/voice mapping | NLP | NLP | 2027-09-23 | 2027-10-02 | 10 | 0% | Not Started | P1 – High | 13.2 | Voice mapping config | Proposed
13.4 | Đánh giá latency / failure / retry | NLP | Testing | 2027-09-27 | 2027-10-06 | 10 | 0% | Not Started | P1 – High | 13.2 | TTS reliability test | Proposed
13.5 | Review accessibility của text + audio output | NLP | Testing | 2027-10-01 | 2027-10-10 | 10 | 0% | Not Started | P1 – High | 13.2,13.3 | Accessibility review note | Proposed
14 | Backend Development | Phase | Cả nhóm | 2027-02-01 | 2027-05-28 | 117 | 0% | Not Started |  |  |  | Proposed phase baseline
14.1 | Decision architecture backend và service boundaries | Backend | Backend | 2027-02-01 | 2027-03-23 | 51 | 0% | Not Started | P0 – Critical | 3.6,1.6 | Backend architecture decision | NestJS/FastAPI là candidates
14.2 | Xây recognition session API | Backend | Backend | 2027-02-14 | 2027-04-05 | 51 | 0% | Not Started | P0 – Critical | 14.1 | Session API | Proposed
14.3 | Thiết kế DB schema cho sessions/model metadata/logs | Backend | Backend | 2027-02-27 | 2027-04-18 | 51 | 0% | Not Started | P0 – Critical | 14.1 | Database schema | PostgreSQL candidate
14.4 | Xây logging/observability model_version + latency + errors | Backend | Backend | 2027-03-12 | 2027-05-01 | 51 | 0% | Not Started | P1 – High | 14.2,14.3 | Observability layer | Bám research reproducibility
14.5 | Xây feedback/correction endpoint | Backend | Backend | 2027-03-26 | 2027-05-15 | 51 | 0% | Not Started | P2 – Medium | 14.2 | Feedback API | Chỉ lưu khi policy/consent cho phép
14.6 | Tích hợp translation/TTS adapter layer | Backend | Backend | 2027-04-08 | 2027-05-28 | 51 | 0% | Not Started | P1 – High | 12.3,13.2,14.1 | Language service integration | Proposed
15 | Frontend Development | Phase | Cả nhóm | 2027-02-15 | 2027-06-21 | 127 | 0% | Not Started |  |  |  | Proposed phase baseline
15.1 | Thiết kế user flow và wireframe research/product modes | Frontend | Frontend | 2027-02-15 | 2027-04-05 | 50 | 0% | Not Started | P1 – High | 1.6 | UI wireframe | Proposed
15.2 | Xây camera capture / preview | Frontend | Frontend | 2027-02-27 | 2027-04-17 | 50 | 0% | Not Started | P0 – Critical | 15.1 | Camera UI module | Proposed
15.3 | Xây recognition session controls | Frontend | Frontend | 2027-03-12 | 2027-04-30 | 50 | 0% | Not Started | P0 – Critical | 15.2,14.2 | Session UI | Proposed
15.4 | Hiển thị gloss / Vietnamese / target output | Frontend | Frontend | 2027-03-25 | 2027-05-13 | 50 | 0% | Not Started | P0 – Critical | 15.3 | Recognition result panel | Core MVP
15.5 | Hiển thị confidence / NO-SIGN / UNKNOWN | Frontend | Frontend | 2027-04-07 | 2027-05-26 | 50 | 0% | Not Started | P0 – Critical | 15.4 | Reliability UI | Core MVP
15.6 | Thêm TTS controls và feedback/history cơ bản | Frontend | Frontend | 2027-04-20 | 2027-06-08 | 50 | 0% | Not Started | P1 – High | 15.4,13.2,14.5 | Output/feedback UI | Proposed
15.7 | Accessibility pass: typography, controls, alternatives | Frontend | Testing | 2027-05-03 | 2027-06-21 | 50 | 0% | Not Started | P1 – High | 15.5,15.6 | Accessibility UI checklist | Proposed
16 | AI–Software Integration | Phase | Cả nhóm | 2027-07-01 | 2027-10-15 | 107 | 0% | Not Started |  |  |  | Proposed phase baseline
16.1 | Chốt model inference contract: input/preprocess/output/version | AI | AI | 2027-07-01 | 2027-08-10 | 41 | 0% | Not Started | P0 – Critical | 9.8,14.1 | Inference contract | Proposed
16.2 | Xây AI inference service | AI | AI | 2027-07-10 | 2027-08-19 | 41 | 0% | Not Started | P0 – Critical | 16.1 | AI service | Python/FastAPI candidate
16.3 | Tích hợp WebSocket/streaming result | Backend | Backend | 2027-07-20 | 2027-08-29 | 41 | 0% | Not Started | P0 – Critical | 16.2,14.2 | Streaming channel | Proposed
16.4 | Tích hợp runtime model candidate vào application | AI | AI | 2027-07-29 | 2027-09-07 | 41 | 0% | Not Started | P0 – Critical | 16.2,16.3,15.3 | Integrated recognition flow | Proposed
16.5 | Tích hợp language layer gloss → Vietnamese | NLP | NLP | 2027-08-08 | 2027-09-17 | 41 | 0% | Not Started | P0 – Critical | 11.6,16.4 | Integrated language flow | Proposed
16.6 | Tích hợp translation + TTS | Backend | Backend | 2027-08-17 | 2027-09-26 | 41 | 0% | Not Started | P1 – High | 12.3,13.2,16.5 | Integrated multilingual output | Proposed
16.7 | Tích hợp end-to-end logging / latency tracing | Backend | Backend | 2027-08-27 | 2027-10-06 | 41 | 0% | Not Started | P1 – High | 14.4,16.4,16.5,16.6 | E2E observability | Proposed
16.8 | Ổn định VSign MVP và freeze feature scope | Integration | Project Lead | 2027-09-05 | 2027-10-15 | 41 | 0% | Not Started | P0 – Critical | 16.4,16.5,16.6,16.7 | VSign MVP candidate | Không thêm stretch trước final evaluation
M09 | Integrated VSign MVP completed | Milestone | Project Lead | 2027-11-15 | 2027-11-15 | 1 | 0% | Not Started | P0 – Critical | 16.8 | Camera→recognition→confidence→gloss→Vietnamese→target/TTS chạy end-to-end | Milestone
17 | Testing | Phase | Cả nhóm | 2027-08-01 | 2027-11-12 | 104 | 0% | Not Started |  |  |  | Proposed phase baseline
17.1 | Unit tests cho preprocessing / normalization / temporal utilities | Testing | QA | 2027-08-01 | 2027-09-10 | 41 | 0% | Not Started | P1 – High | 6.2,10.4 | Unit test suite | Proposed
17.2 | Data validation tests: labels / duplicate / signer leakage | Testing | QA | 2027-08-11 | 2027-09-20 | 41 | 0% | Not Started | P0 – Critical | 6.5,6.6 | Dataset validation tests | Proposed
17.3 | Model regression tests trên fixed validation set | Testing | QA | 2027-08-22 | 2027-10-01 | 41 | 0% | Not Started | P1 – High | 9.8 | Model regression suite | Proposed
17.4 | API integration tests cho session/inference/language | Testing | QA | 2027-09-01 | 2027-10-11 | 41 | 0% | Not Started | P1 – High | 16.7 | API integration suite | Proposed
17.5 | E2E scenario tests từ camera đến output | Testing | QA | 2027-09-12 | 2027-10-22 | 41 | 0% | Not Started | P0 – Critical | 16.8 | E2E test report | Proposed
17.6 | Privacy/security checks cho video/log/artifacts | Testing | QA | 2027-09-23 | 2027-11-02 | 41 | 0% | Not Started | P1 – High | 16.8 | Privacy/security checklist | Proposed
17.7 | Accessibility/usability checks | Testing | QA | 2027-10-03 | 2027-11-12 | 41 | 0% | Not Started | P1 – High | 15.7,16.8 | Usability/accessibility test notes | Proposed
18 | Performance & Robustness Evaluation | Phase | Cả nhóm | 2027-04-01 | 2027-10-31 | 214 | 0% | Not Started |  |  |  | Proposed phase baseline
18.1 | Xây benchmark harness thống nhất cho accuracy/latency/resource | Research | Research | 2027-04-01 | 2027-06-21 | 82 | 0% | Not Started | P0 – Critical | 3.4,7.6 | Benchmark harness | Proposed
18.2 | Đo FPS và model latency p50/p95 | AI | AI | 2027-04-19 | 2027-07-09 | 82 | 0% | Not Started | P0 – Critical | 18.1,9.8 | Runtime latency report | RQ5
18.3 | Đo end-to-end latency và resource profile | Research | Testing | 2027-05-08 | 2027-07-28 | 82 | 0% | Not Started | P0 – Critical | 18.1,16.8 | E2E performance report | RQ5
18.4 | Chạy robustness: lighting/view/distance/speed/handedness | Research | Research | 2027-05-27 | 2027-08-16 | 82 | 0% | Not Started | P0 – Critical | 18.1,5.5,9.8 | Robustness report | RQ4
18.5 | Đánh giá NO-SIGN/UNKNOWN false accept / false reject | Research | Research | 2027-06-15 | 2027-09-04 | 82 | 0% | Not Started | P0 – Critical | 10.4,16.8 | Reliability report | E7
18.6 | Tune confidence threshold trên validation, không dùng final test | AI | AI | 2027-07-04 | 2027-09-23 | 82 | 0% | Not Started | P1 – High | 18.5 | Threshold configuration | Tránh test leakage
18.7 | Chạy final holdout evaluation một lần sau khi freeze | Research | Research | 2027-07-23 | 2027-10-12 | 82 | 0% | Not Started | P0 – Critical | 18.2,18.3,18.4,18.5,18.6 | Final evaluation results | Không tune trên final test
18.8 | Tổng hợp error analysis và limitations | Documentation | Documentation | 2027-08-11 | 2027-10-31 | 82 | 0% | Not Started | P0 – Critical | 18.7 | Final error analysis | Phải ghi cả failure cases
M10 | Final evaluation completed | Milestone | Research | 2027-12-31 | 2027-12-31 | 1 | 0% | Not Started | P0 – Critical | 18.8 | Holdout evaluation, robustness, latency, no-sign reliability và error analysis hoàn thành | Milestone
19 | Deployment | Phase | Cả nhóm | 2027-11-01 | 2027-12-28 | 58 | 0% | Not Started |  |  |  | Proposed phase baseline
19.1 | Containerize application + AI services | Deployment | Deployment | 2027-11-01 | 2027-11-25 | 25 | 0% | Not Started | P1 – High | 16.8 | Dockerized prototype | Docker Compose candidate
19.2 | Chuẩn hóa environment/config/secrets | Deployment | Deployment | 2027-11-07 | 2027-12-01 | 25 | 0% | Not Started | P1 – High | 19.1 | Environment config | Proposed
19.3 | Đóng gói model artifacts + version mapping | AI | AI | 2027-11-14 | 2027-12-08 | 25 | 0% | Not Started | P1 – High | 19.1,9.8 | Release model package | Proposed
19.4 | Deploy staging/demo environment | Deployment | Deployment | 2027-11-21 | 2027-12-15 | 25 | 0% | Not Started | P0 – Critical | 19.1,19.2,19.3 | Demo deployment | Proposed
19.5 | Viết Deployment Guide / runbook | Documentation | Documentation | 2027-11-27 | 2027-12-21 | 25 | 0% | Not Started | P1 – High | 19.4 | Deployment Guide | Proposed
19.6 | Chuẩn bị backup demo/video và offline fallback | Documentation | Documentation | 2027-12-04 | 2027-12-28 | 25 | 0% | Not Started | P1 – High | 19.4 | Demo backup package | Proposed
20 | Research Paper | Phase | Cả nhóm | 2027-06-01 | 2027-12-08 | 191 | 0% | Not Started |  |  |  | Proposed phase baseline
20.1 | Chốt paper outline và contribution claims | Research | Research | 2027-06-01 | 2027-08-12 | 73 | 0% | Not Started | P1 – High | 9.7,18.1 | Paper outline | Claims phải bám evidence
20.2 | Viết Methodology: data, Model A/B/C, transfer protocol | Research | Research | 2027-06-17 | 2027-08-28 | 73 | 0% | Not Started | P0 – Critical | 20.1,9.8 | Methods draft | Proposed
20.3 | Viết Dataset/Evaluation protocol section | Dataset | Dataset | 2027-07-04 | 2027-09-14 | 73 | 0% | Not Started | P1 – High | 20.1,6.7,18.1 | Data & evaluation draft | Proposed
20.4 | Viết Experiments: E2–E8 và implementation details | Research | Research | 2027-07-21 | 2027-10-01 | 73 | 0% | Not Started | P0 – Critical | 20.2,20.3,18.7 | Experiments draft | Proposed
20.5 | Viết Results + error analysis + learning curves | Research | Research | 2027-08-07 | 2027-10-18 | 73 | 0% | Not Started | P0 – Critical | 20.4,18.7,18.8 | Results draft | Proposed
20.6 | Viết Discussion, limitations, ethics/accessibility | Documentation | Documentation | 2027-08-24 | 2027-11-04 | 73 | 0% | Not Started | P1 – High | 20.5 | Discussion draft | Không phóng đại
20.7 | Hoàn thiện Related Work từ Literature Matrix | Research | Research | 2027-09-10 | 2027-11-21 | 73 | 0% | Not Started | P1 – High | 2.6,20.5 | Related Work final | Proposed
20.8 | Tạo full paper draft và internal review | Documentation | Documentation | 2027-09-27 | 2027-12-08 | 73 | 0% | Not Started | P0 – Critical | 20.2,20.3,20.4,20.5,20.6,20.7 | Research paper draft | Proposed
M11 | Research paper draft completed | Milestone | Research | 2028-01-31 | 2028-01-31 | 1 | 0% | Not Started | P0 – Critical | 20.8 | Full paper draft được internal review | Milestone
21 | Final Report & Presentation | Phase | Cả nhóm | 2028-01-01 | 2028-02-15 | 46 | 0% | Not Started |  |  |  | Proposed phase baseline
21.1 | Chốt cấu trúc Final Report theo yêu cầu trường/đề tài | Documentation | Documentation | 2028-01-01 | 2028-01-18 | 18 | 0% | Not Started | P1 – High | 20.8 | Final report outline | TBD theo form chính thức
21.2 | Cập nhật architecture diagrams / WBS / experiment tables | Documentation | Documentation | 2028-01-05 | 2028-01-22 | 18 | 0% | Not Started | P1 – High | 18.8,19.5 | Final figures/tables | Proposed
21.3 | Lập traceability Objective → Experiment → Result → Conclusion | Research | Research | 2028-01-09 | 2028-01-26 | 18 | 0% | Not Started | P0 – Critical | 18.7,20.8 | Traceability matrix | Proposed
21.4 | Hoàn thiện Final Report | Documentation | Documentation | 2028-01-13 | 2028-01-30 | 18 | 0% | Not Started | P0 – Critical | 21.1,21.2,21.3 | Final Report | Proposed
21.5 | Chuẩn bị slide bảo vệ | Documentation | Documentation | 2028-01-17 | 2028-02-03 | 18 | 0% | Not Started | P1 – High | 21.4 | Presentation deck | Proposed
21.6 | Chuẩn bị demo script + contingency plan | Final Deliverables | Project Lead | 2028-01-21 | 2028-02-07 | 18 | 0% | Not Started | P1 – High | 19.6,21.5 | Demo script | Proposed
21.7 | Rehearsal / Q&A / fix cuối | Final Deliverables | Cả nhóm | 2028-01-25 | 2028-02-11 | 18 | 0% | Not Started | P0 – Critical | 21.5,21.6 | Defense readiness checklist | Proposed
21.8 | Archive source/model/data docs và final deliverables | Documentation | Documentation | 2028-01-29 | 2028-02-15 | 18 | 0% | Not Started | P1 – High | 21.4,21.7 | Final archive package | Proposed
M12 | Final project completed | Milestone | Project Lead | 2028-02-29 | 2028-02-29 | 1 | 0% | Not Started | P0 – Critical | 21.8 | Final report, presentation, demo, archive và defense readiness hoàn thành | Milestone
Formulas:
Ngày bắt đầu = MIN([Ngày bắt đầu, row below]:E14)
Ngày kết thúc = MAX([Ngày kết thúc, row below]:F14)
TÊN TRƯỜNG = IF(H8>=1,"Completed",IF(TODAY()<[Ngày bắt đầu],"Not Started",IF(TODAY()>[Ngày kết thúc],"Delayed","In Progress")))
TÊN TRƯỜNG = IF(H15>=1,"Completed",IF(TODAY()>[Ngày kết thúc],"Delayed",IF(TODAY()=[Ngày kết thúc],"Review","Not Started")))

## 02_MILESTONES
VSIGN — MILESTONES
Các Target Date dưới đây là Proposed baseline và liên kết với 01_MASTER_GANTT. Acceptance Criteria phản ánh hướng đề tài đã chốt.
Milestone ID | Milestone | Target Date | Related Phase | Acceptance Criteria | Owner | Status
M01 | Project direction baseline locked | 2026-09-30 | 1 — Project Definition & Research Direction | Tên đề tài, research story, Project Overview và Master Gantt baseline được chốt | Project Lead | Completed
M02 | Literature review & research gap completed | 2026-10-31 | 2 — Literature Review | Literature Matrix + Research Gap Analysis đủ để khóa proposal | Research | Not Started
M03 | Research design / proposal approved | 2026-11-15 | 3 — Research Design | RQ1–RQ6, E1–E8, evaluation protocol và proposal được duyệt | Research | Not Started
M04 | Dataset protocol completed | 2026-11-30 | 4 — VSL Dataset Planning | Vocabulary, source/access, metadata, signer split, consent/collection protocol sẵn sàng | Dataset | Not Started
M05 | Dataset v1 + signer split ready | 2027-03-31 | 6 — Data Processing & Annotation | Dataset v1, QC, leakage audit, signer-independent split và Dataset Card v1 hoàn thành | Dataset | Not Started
M06 | Model A/B baselines completed | 2027-05-15 | 8 — Signer-independent Recognition | Baseline metrics và unseen-signer evaluation cho landmark models hoàn thành | AI | Not Started
M07 | Core TL/data-efficiency/generalization experiments completed | 2027-07-31 | 9 — Model Improvement & Experimentation | E2–E6 hoàn thành; research/runtime candidate được chọn | AI | Not Started
M08 | Short-sequence + language target reached | 2027-10-15 | 11 — Gloss-to-Vietnamese NLP | 2–5 gloss target và gloss→Vietnamese layer có evaluation/limitations rõ | AI / NLP | Not Started
M09 | Integrated VSign MVP completed | 2027-11-15 | 16 — AI–Software Integration | Camera→recognition→confidence→gloss→Vietnamese→target/TTS chạy end-to-end | Project Lead | Not Started
M10 | Final evaluation completed | 2027-12-31 | 18 — Performance & Robustness Evaluation | Holdout evaluation, robustness, latency, no-sign reliability và error analysis hoàn thành | Research | Not Started
M11 | Research paper draft completed | 2028-01-31 | 20 — Research Paper | Full paper draft được internal review | Research | Not Started
M12 | Final project completed | 2028-02-29 | 21 — Final Report & Presentation | Final report, presentation, demo, archive và defense readiness hoàn thành | Project Lead | Not Started

## 03_TASK_TRACKER
VSIGN — TASK TRACKER
Linked view từ 01_MASTER_GANTT. Source of truth: cập nhật task dates / % complete / priority / owner trên 01_MASTER_GANTT; dùng cột Blocker tại đây để ghi vấn đề hằng tuần.
Task ID | Task | Workstream | Owner | Priority | Start | Due | Status | % Complete | Dependency | Blocker | Deliverable | Notes
1.1 | Khóa tên đề tài chính thức và research positioning | Project Management | Project Lead | P0 – Critical | 2026-09-01 | 2026-09-10 | Completed | 100% |  |  | Project title + research positioning | Đã chốt theo baseline 21/09/2026
1.2 | Xác nhận research story: low-resource VSL → transfer learning → data efficiency → signer generalization → robust real-time recognition | Research | Research | P0 – Critical | 2026-09-05 | 2026-09-14 | Completed | 100% | 1.1 |  | Research direction statement | Đã chốt
1.3 | Hoàn thiện VSign Project Overview v0.1 theo hướng đã chốt | Documentation | Documentation | P0 – Critical | 2026-09-09 | 2026-09-18 | Completed | 100% | 1.2 |  | VSign Project Overview v0.1 | Đã hoàn thiện trong project
1.4 | Xây Master Gantt/WBS và hệ thống theo dõi tiến độ | Project Management | Project Lead | P1 – High | 2026-09-13 | 2026-09-22 | Completed | 100% | 1.3 |  | VSign Project Master Gantt | Proposed baseline; file hiện tại
1.5 | Thiết lập Decision Log / Risk Register / Issue Log | Project Management | Project Lead | P1 – High | 2026-09-17 | 2026-09-26 | In Progress | 0% | 1.4 |  | Governance templates | Proposed
1.6 | Chốt kiến trúc tài liệu và quy tắc change control | Documentation | Documentation | P1 – High | 2026-09-21 | 2026-09-30 | In Progress | 0% | 1.3 |  | Documentation governance note | Proposed
2.1 | Thu thập literature VSL/SLR giai đoạn nền tảng và gần đây | Research | Research | P0 – Critical | 2026-09-07 | 2026-09-24 | In Progress | 0% | 1.2 |  | Core paper library | Ưu tiên VSL + CSLR + transfer learning
2.2 | Đọc và tóm tắt VSL Review 2026, VSL400 2026, CrossViViT 2025, Camgoz 2020 và các công trình liên quan | Research | Research | P0 – Critical | 2026-09-11 | 2026-09-28 | In Progress | 0% | 2.1 |  | Paper summaries | Current evidence base
2.3 | Lập Literature Matrix: dataset, signers, input, model, split, metric, limitation | Research | Research | P1 – High | 2026-09-16 | 2026-10-03 | In Progress | 0% | 2.2 |  | Literature Matrix | Proposed
2.4 | Tổng hợp hướng community / real-world / accessibility để nhận diện khoảng cách lab–deployment | Research | Research | P2 – Medium | 2026-09-21 | 2026-10-08 | In Progress | 0% | 2.2 |  | Community & deployment notes | Nguồn ngoài literature chỉ dùng bổ trợ
2.5 | Phân tích research gap và novelty phù hợp VSign | Research | Research | P0 – Critical | 2026-09-26 | 2026-10-13 | Not Started | 0% | 2.3 |  | VSign Research Gap Analysis | Không khóa novelty nếu evidence chưa đủ
2.6 | Viết Literature Review bản 1 | Documentation | Documentation | P1 – High | 2026-10-01 | 2026-10-18 | Not Started | 0% | 2.5 |  | Literature Review draft | Proposed
3.1 | Khóa Research Questions RQ1–RQ6 ở mức proposal | Research | Research | P0 – Critical | 2026-10-01 | 2026-10-15 | Not Started | 0% | 2.5 |  | Research Questions set | Bám baseline hiện tại
3.2 | Xác định hypotheses / expected comparisons không gắn KPI tùy ý | Research | Research | P1 – High | 2026-10-05 | 2026-10-19 | Not Started | 0% | 3.1 |  | Hypothesis table | Proposed
3.3 | Chốt Experiment Matrix E1–E8; E9 optional | Research | Research | P0 – Critical | 2026-10-09 | 2026-10-23 | Not Started | 0% | 3.1 |  | Experiment Matrix | Bám current direction
3.4 | Thiết kế Evaluation Protocol: Accuracy, Macro-F1, GER, latency, resource, reliability | Research | Research | P0 – Critical | 2026-10-13 | 2026-10-27 | Not Started | 0% | 3.3 |  | Evaluation Protocol draft | Không dùng accuracy duy nhất
3.5 | Thiết kế reproducibility protocol: seeds, configs, model/data version, experiment tracking | AI | AI | P1 – High | 2026-10-17 | 2026-10-31 | Not Started | 0% | 3.4 |  | Reproducibility checklist | Proposed
3.6 | Hoàn thiện Research Proposal | Documentation | Documentation | P0 – Critical | 2026-10-21 | 2026-11-04 | Not Started | 0% | 3.1,3.3,3.4 |  | VSign Research Proposal | Proposed
4.1 | Xác minh điều kiện truy cập / Data Usage Agreement của VSL400 | Dataset | Dataset | P0 – Critical | 2026-10-15 | 2026-10-28 | Not Started | 0% | 2.2 |  | VSL400 access decision | VSL400 là controlled access; không giả định đã có quyền
4.2 | Chốt tiêu chí vocabulary MVP 30–50 gloss | Dataset | Dataset | P0 – Critical | 2026-10-19 | 2026-11-01 | Not Started | 0% | 3.1 |  | MVP vocabulary criteria | 30–50 là scope đã chốt ở mức Overview
4.3 | Xây danh sách vocabulary MVP dự kiến | Dataset | Dataset | P1 – High | 2026-10-23 | 2026-11-05 | Not Started | 0% | 4.2 |  | MVP vocabulary v0 | Cần VSL expert review nếu khả thi
4.4 | Xác định benchmark subset 100–400 classes nếu dữ liệu/tài nguyên cho phép | Research | Research | P2 – Medium | 2026-10-27 | 2026-11-09 | Not Started | 0% | 4.1 |  | Benchmark subset plan | Không bắt buộc MVP
4.5 | Thiết kế metadata schema: signer/session/handedness/view/lighting/speed/quality | Dataset | Dataset | P0 – Critical | 2026-10-31 | 2026-11-13 | Not Started | 0% | 4.2 |  | Dataset schema | Bám robustness & generalization RQ
4.6 | Thiết kế signer-independent split và leakage-check protocol | Dataset | Dataset | P0 – Critical | 2026-11-04 | 2026-11-17 | Not Started | 0% | 4.5 |  | Split protocol | Bắt buộc cho claim generalization
4.7 | Soạn self-collection / consent / storage protocol | Dataset | Dataset | P0 – Critical | 2026-11-08 | 2026-11-21 | Not Started | 0% | 4.5 |  | Collection & consent protocol | TBD policy phải được phê duyệt trước collection chính thức
5.1 | Nhập metadata và tài nguyên VSL400 được cấp quyền (nếu truy cập được) | Dataset | Dataset | P0 – Critical | 2026-11-15 | 2026-12-20 | Not Started | 0% | 4.1 |  | Imported external dataset inventory | Phụ thuộc access
5.2 | Tuyển người ký và hoàn tất consent nếu cần tự thu | Dataset | Dataset | P0 – Critical | 2026-11-24 | 2026-12-29 | Not Started | 0% | 4.7 |  | Signer roster + consent records | Ưu tiên diversity
5.3 | Chạy pilot recording để kiểm tra protocol | Dataset | Dataset | P1 – High | 2026-12-03 | 2027-01-07 | Not Started | 0% | 5.2 |  | Pilot recording report | Proposed
5.4 | Thu dữ liệu vòng 1 cho vocabulary MVP | Dataset | Dataset | P0 – Critical | 2026-12-13 | 2027-01-17 | Not Started | 0% | 5.3 |  | Self-collected raw data v0 | Ưu tiên nhiều signer hơn nhiều repetition từ ít signer
5.5 | Thu mẫu robustness có kiểm soát: view/lighting/speed/handedness/occlusion | Dataset | Dataset | P1 – High | 2026-12-22 | 2027-01-26 | Not Started | 0% | 5.4 |  | Robustness subset | Phục vụ RQ4/E6
5.6 | Kiểm kê completeness, backup và access permissions | Dataset | Dataset | P1 – High | 2026-12-31 | 2027-02-04 | Not Started | 0% | 5.4,5.5 |  | Collection QC report | Proposed
6.1 | Thiết lập cấu trúc thư mục, dataset manifest và versioning | Dataset | Dataset | P0 – Critical | 2026-12-01 | 2027-01-05 | Not Started | 0% | 5.1,5.4 |  | Dataset pipeline v0 | Proposed
6.2 | Chuẩn hóa video/frame sampling và quality checks | Dataset | Dataset | P1 – High | 2026-12-10 | 2027-01-14 | Not Started | 0% | 6.1 |  | Preprocessed video set | Candidate preprocessing; chưa khóa tool
6.3 | Trích xuất hand/pose/selected-face landmarks | AI | AI | P0 – Critical | 2026-12-19 | 2027-01-23 | Not Started | 0% | 6.2 |  | Landmark feature set | MediaPipe là candidate
6.4 | Rà soát / gán nhãn gloss và metadata | Dataset | Dataset | P0 – Critical | 2026-12-29 | 2027-02-02 | Not Started | 0% | 6.2 |  | Verified labels | Cần review domain khi khả thi
6.5 | Deduplicate và kiểm tra signer/session leakage | Dataset | Dataset | P0 – Critical | 2027-01-07 | 2027-02-11 | Not Started | 0% | 6.4 |  | Leakage audit | Bắt buộc trước final split
6.6 | Tạo train/validation/test split theo signer | Dataset | Dataset | P0 – Critical | 2027-01-16 | 2027-02-20 | Not Started | 0% | 6.5 |  | Signer-independent split v1 | Core evaluation asset
6.7 | Tạo Dataset Card v1 và statistics report | Documentation | Documentation | P1 – High | 2027-01-26 | 2027-03-02 | Not Started | 0% | 6.6 |  | Dataset Card v1 | Proposed
7.1 | Xây Model A: hand landmarks + LSTM baseline | AI | AI | P0 – Critical | 2027-01-01 | 2027-01-25 | Not Started | 0% | 6.3,6.6 |  | Model A v1 | Engineering baseline
7.2 | So sánh LSTM với GRU/TCN lightweight baseline | AI | AI | P1 – High | 2027-01-07 | 2027-01-31 | Not Started | 0% | 7.1 |  | E1 baseline comparison | Phục vụ E1
7.3 | Xây Model B: hand + pose temporal baseline | AI | AI | P0 – Critical | 2027-01-14 | 2027-02-07 | Not Started | 0% | 6.3,6.6 |  | Model B HP v1 | Phục vụ RQ3
7.4 | Mở rộng Model B: hand + pose + selected face | AI | AI | P1 – High | 2027-01-20 | 2027-02-13 | Not Started | 0% | 7.3 |  | Model B HPF v1 | Selected face, không mặc định toàn bộ face landmarks
7.5 | Đánh giá baseline: Accuracy/Macro-F1/confusion matrix | Research | Research | P0 – Critical | 2027-01-27 | 2027-02-20 | Not Started | 0% | 7.1,7.3,7.4 |  | Baseline evaluation report | Proposed
7.6 | Profile inference baseline: FPS, p50/p95 latency, RAM/VRAM | AI | AI | P1 – High | 2027-02-02 | 2027-02-26 | Not Started | 0% | 7.5 |  | Baseline performance profile | Real-time evidence
8.1 | Xây signer-independent dataloader/evaluation pipeline cố định | AI | AI | P0 – Critical | 2027-03-01 | 2027-03-25 | Not Started | 0% | 6.6 |  | Signer-independent evaluation pipeline | Không dùng random split cho claim generalization
8.2 | Chạy seen-signer benchmark cho Model A/B | AI | AI | P2 – Medium | 2027-03-07 | 2027-03-31 | Not Started | 0% | 8.1,7.5 |  | Seen-signer reference results | Chỉ để đối chiếu
8.3 | Chạy unseen-signer benchmark cho Model A | AI | AI | P0 – Critical | 2027-03-14 | 2027-04-07 | Not Started | 0% | 8.1,7.1 |  | Model A unseen-signer results | Core metric
8.4 | Chạy unseen-signer benchmark cho Model B | AI | AI | P0 – Critical | 2027-03-21 | 2027-04-14 | Not Started | 0% | 8.1,7.3,7.4 |  | Model B unseen-signer results | Core metric
8.5 | Phân tích per-signer và gesture-pair failures | Research | Research | P1 – High | 2027-03-27 | 2027-04-20 | Not Started | 0% | 8.3,8.4 |  | Generalization error analysis | Proposed
8.6 | So sánh random split vs signer-independent chỉ để minh họa leakage | Research | Research | P2 – Medium | 2027-04-03 | 2027-04-27 | Not Started | 0% | 8.1 |  | Leakage illustration | Không dùng random split làm kết luận chính
9.1 | Chọn pretrained RGB/video backbone candidate | AI | AI | P0 – Critical | 2027-04-01 | 2027-05-06 | Not Started | 0% | 2.2,7.5 |  | Model C architecture decision | CrossViViT/video Transformer là evidence, không mặc định best
9.2 | Triển khai Model C cùng architecture với random initialization | AI | AI | P0 – Critical | 2027-04-09 | 2027-05-14 | Not Started | 0% | 9.1,6.6 |  | Model C Scratch | Control arm cho E3
9.3 | Triển khai Model C với pretrained initialization + fine-tuning | AI | AI | P0 – Critical | 2027-04-17 | 2027-05-22 | Not Started | 0% | 9.1,6.6 |  | Model C Pretrained | Treatment arm cho E3
9.4 | Chạy E3: Scratch vs Pretrained trên cùng input/split/protocol | Research | Research | P0 – Critical | 2027-04-26 | 2027-05-31 | Not Started | 0% | 9.2,9.3 |  | E3 Transfer Learning report | Core contribution
9.5 | Chạy E4: 10/25/50/75/100% labeled training data | Research | Research | P0 – Critical | 2027-05-04 | 2027-06-08 | Not Started | 0% | 9.2,9.3 |  | Data-efficiency learning curves | Core contribution
9.6 | Tổng hợp E2 representation ablation Hand vs HP vs HPF | Research | Research | P1 – High | 2027-05-13 | 2027-06-17 | Not Started | 0% | 7.5,8.4 |  | E2 representation report | RQ3
9.7 | Chạy E5/E6: unseen signer + robustness conditions | Research | Research | P0 – Critical | 2027-05-21 | 2027-06-25 | Not Started | 0% | 8.3,8.4,5.5,9.3 |  | Generalization & robustness report | RQ4
9.8 | Chọn research model và runtime candidate dựa trên accuracy–latency–resource | AI | AI | P0 – Critical | 2027-05-29 | 2027-07-03 | Not Started | 0% | 9.4,9.5,9.7 |  | Model selection decision | Có thể khác nhau giữa research và runtime
10.1 | Thiết kế short-sequence vocabulary / templates 2–5 gloss | Research | Research | P1 – High | 2027-08-01 | 2027-08-22 | Not Started | 0% | 4.3,9.8 |  | Short-sequence scope | Target sau core recognition
10.2 | Chuẩn bị / thu short-sequence samples | Dataset | Dataset | P1 – High | 2027-08-06 | 2027-08-27 | Not Started | 0% | 10.1,5.4 |  | Short-sequence dataset v0 | Proposed
10.3 | Triển khai streaming sliding window + no-sign/blank state | AI | AI | P0 – Critical | 2027-08-12 | 2027-09-02 | Not Started | 0% | 10.2,9.8 |  | Streaming decoder v1 | Target
10.4 | Triển khai duplicate suppression và temporal stability | AI | AI | P0 – Critical | 2027-08-18 | 2027-09-08 | Not Started | 0% | 10.3 |  | Temporal stabilization v1 | Phục vụ E7
10.5 | Đánh giá short-sequence bằng Gloss Error Rate | Research | Research | P1 – High | 2027-08-24 | 2027-09-14 | Not Started | 0% | 10.3,10.4 |  | Short-sequence evaluation | Target
10.6 | Decision gate: có đủ dữ liệu để thử full CSLR/CTC hay không | AI | Project Lead | P0 – Critical | 2027-08-30 | 2027-09-20 | Not Started | 0% | 10.5 |  | CSLR go/no-go decision | Không để full continuous chặn MVP
10.7 | Prototype CTC / continuous nếu gate = GO | AI | AI | P3 – Low | 2027-09-05 | 2027-09-26 | Not Started | 0% | 10.6 |  | Optional CSLR prototype | Stretch only
11.1 | Chuẩn hóa gloss inventory và mapping rules | NLP | NLP | P0 – Critical | 2027-07-01 | 2027-07-26 | Not Started | 0% | 4.3,6.4 |  | Gloss language map | Proposed
11.2 | Xây rule/template gloss → Vietnamese baseline | NLP | NLP | P0 – Critical | 2027-07-07 | 2027-08-01 | Not Started | 0% | 11.1 |  | Language baseline v1 | Core language layer
11.3 | Thử constrained generation candidate nếu cần | NLP | NLP | P2 – Medium | 2027-07-14 | 2027-08-08 | Not Started | 0% | 11.2 |  | Constrained generator prototype | Không để LLM che lỗi recognition
11.4 | Xây semantic preservation / adequacy evaluation set | Research | Research | P1 – High | 2027-07-21 | 2027-08-15 | Not Started | 0% | 11.1 |  | Language evaluation set | Proposed
11.5 | Chạy E8: ground-truth gloss vs predicted gloss → Vietnamese | Research | Research | P0 – Critical | 2027-07-28 | 2027-08-22 | Not Started | 0% | 11.2,11.4,9.7 |  | Error-propagation report v1 | RQ6
11.6 | Chọn language layer cho MVP | NLP | NLP | P0 – Critical | 2027-08-04 | 2027-08-29 | Not Started | 0% | 11.2,11.3,11.5 |  | Language layer decision | Evidence-based
12.1 | Chốt target language MVP đầu tiên | NLP | Project Lead | P1 – High | 2027-09-01 | 2027-09-10 | Not Started | 0% | 11.6 |  | Target language decision | English là Proposed, chưa mặc định nếu team chọn khác
12.2 | Chọn translation provider/model candidate | NLP | NLP | P1 – High | 2027-09-05 | 2027-09-14 | Not Started | 0% | 12.1 |  | Translation decision record | Không tự train từ đầu
12.3 | Xây translation interface Vietnamese → target | NLP | NLP | P0 – Critical | 2027-09-09 | 2027-09-18 | Not Started | 0% | 12.2 |  | Translation adapter | Modular service
12.4 | Đánh giá câu ngắn: adequacy/obvious failures/latency | Research | Research | P1 – High | 2027-09-13 | 2027-09-22 | Not Started | 0% | 12.3 |  | Translation evaluation notes | Integration-level evaluation
12.5 | Thêm fallback / timeout / cache policy khi phù hợp | Backend | Backend | P2 – Medium | 2027-09-17 | 2027-09-26 | Not Started | 0% | 12.3 |  | Translation reliability logic | Proposed
13.1 | Chọn TTS provider/model/voice candidate | NLP | NLP | P1 – High | 2027-09-15 | 2027-09-24 | Not Started | 0% | 12.1 |  | TTS decision record | TBD provider
13.2 | Xây TTS interface target text → audio | Backend | Backend | P0 – Critical | 2027-09-19 | 2027-09-28 | Not Started | 0% | 13.1 |  | TTS adapter | Integration layer
13.3 | Xử lý language/voice mapping | NLP | NLP | P1 – High | 2027-09-23 | 2027-10-02 | Not Started | 0% | 13.2 |  | Voice mapping config | Proposed
13.4 | Đánh giá latency / failure / retry | NLP | Testing | P1 – High | 2027-09-27 | 2027-10-06 | Not Started | 0% | 13.2 |  | TTS reliability test | Proposed
13.5 | Review accessibility của text + audio output | NLP | Testing | P1 – High | 2027-10-01 | 2027-10-10 | Not Started | 0% | 13.2,13.3 |  | Accessibility review note | Proposed
14.1 | Decision architecture backend và service boundaries | Backend | Backend | P0 – Critical | 2027-02-01 | 2027-03-23 | Not Started | 0% | 3.6,1.6 |  | Backend architecture decision | NestJS/FastAPI là candidates
14.2 | Xây recognition session API | Backend | Backend | P0 – Critical | 2027-02-14 | 2027-04-05 | Not Started | 0% | 14.1 |  | Session API | Proposed
14.3 | Thiết kế DB schema cho sessions/model metadata/logs | Backend | Backend | P0 – Critical | 2027-02-27 | 2027-04-18 | Not Started | 0% | 14.1 |  | Database schema | PostgreSQL candidate
14.4 | Xây logging/observability model_version + latency + errors | Backend | Backend | P1 – High | 2027-03-12 | 2027-05-01 | Not Started | 0% | 14.2,14.3 |  | Observability layer | Bám research reproducibility
14.5 | Xây feedback/correction endpoint | Backend | Backend | P2 – Medium | 2027-03-26 | 2027-05-15 | Not Started | 0% | 14.2 |  | Feedback API | Chỉ lưu khi policy/consent cho phép
14.6 | Tích hợp translation/TTS adapter layer | Backend | Backend | P1 – High | 2027-04-08 | 2027-05-28 | Not Started | 0% | 12.3,13.2,14.1 |  | Language service integration | Proposed
15.1 | Thiết kế user flow và wireframe research/product modes | Frontend | Frontend | P1 – High | 2027-02-15 | 2027-04-05 | Not Started | 0% | 1.6 |  | UI wireframe | Proposed
15.2 | Xây camera capture / preview | Frontend | Frontend | P0 – Critical | 2027-02-27 | 2027-04-17 | Not Started | 0% | 15.1 |  | Camera UI module | Proposed
15.3 | Xây recognition session controls | Frontend | Frontend | P0 – Critical | 2027-03-12 | 2027-04-30 | Not Started | 0% | 15.2,14.2 |  | Session UI | Proposed
15.4 | Hiển thị gloss / Vietnamese / target output | Frontend | Frontend | P0 – Critical | 2027-03-25 | 2027-05-13 | Not Started | 0% | 15.3 |  | Recognition result panel | Core MVP
15.5 | Hiển thị confidence / NO-SIGN / UNKNOWN | Frontend | Frontend | P0 – Critical | 2027-04-07 | 2027-05-26 | Not Started | 0% | 15.4 |  | Reliability UI | Core MVP
15.6 | Thêm TTS controls và feedback/history cơ bản | Frontend | Frontend | P1 – High | 2027-04-20 | 2027-06-08 | Not Started | 0% | 15.4,13.2,14.5 |  | Output/feedback UI | Proposed
15.7 | Accessibility pass: typography, controls, alternatives | Frontend | Testing | P1 – High | 2027-05-03 | 2027-06-21 | Not Started | 0% | 15.5,15.6 |  | Accessibility UI checklist | Proposed
16.1 | Chốt model inference contract: input/preprocess/output/version | AI | AI | P0 – Critical | 2027-07-01 | 2027-08-10 | Not Started | 0% | 9.8,14.1 |  | Inference contract | Proposed
16.2 | Xây AI inference service | AI | AI | P0 – Critical | 2027-07-10 | 2027-08-19 | Not Started | 0% | 16.1 |  | AI service | Python/FastAPI candidate
16.3 | Tích hợp WebSocket/streaming result | Backend | Backend | P0 – Critical | 2027-07-20 | 2027-08-29 | Not Started | 0% | 16.2,14.2 |  | Streaming channel | Proposed
16.4 | Tích hợp runtime model candidate vào application | AI | AI | P0 – Critical | 2027-07-29 | 2027-09-07 | Not Started | 0% | 16.2,16.3,15.3 |  | Integrated recognition flow | Proposed
16.5 | Tích hợp language layer gloss → Vietnamese | NLP | NLP | P0 – Critical | 2027-08-08 | 2027-09-17 | Not Started | 0% | 11.6,16.4 |  | Integrated language flow | Proposed
16.6 | Tích hợp translation + TTS | Backend | Backend | P1 – High | 2027-08-17 | 2027-09-26 | Not Started | 0% | 12.3,13.2,16.5 |  | Integrated multilingual output | Proposed
16.7 | Tích hợp end-to-end logging / latency tracing | Backend | Backend | P1 – High | 2027-08-27 | 2027-10-06 | Not Started | 0% | 14.4,16.4,16.5,16.6 |  | E2E observability | Proposed
16.8 | Ổn định VSign MVP và freeze feature scope | Integration | Project Lead | P0 – Critical | 2027-09-05 | 2027-10-15 | Not Started | 0% | 16.4,16.5,16.6,16.7 |  | VSign MVP candidate | Không thêm stretch trước final evaluation
17.1 | Unit tests cho preprocessing / normalization / temporal utilities | Testing | QA | P1 – High | 2027-08-01 | 2027-09-10 | Not Started | 0% | 6.2,10.4 |  | Unit test suite | Proposed
17.2 | Data validation tests: labels / duplicate / signer leakage | Testing | QA | P0 – Critical | 2027-08-11 | 2027-09-20 | Not Started | 0% | 6.5,6.6 |  | Dataset validation tests | Proposed
17.3 | Model regression tests trên fixed validation set | Testing | QA | P1 – High | 2027-08-22 | 2027-10-01 | Not Started | 0% | 9.8 |  | Model regression suite | Proposed
17.4 | API integration tests cho session/inference/language | Testing | QA | P1 – High | 2027-09-01 | 2027-10-11 | Not Started | 0% | 16.7 |  | API integration suite | Proposed
17.5 | E2E scenario tests từ camera đến output | Testing | QA | P0 – Critical | 2027-09-12 | 2027-10-22 | Not Started | 0% | 16.8 |  | E2E test report | Proposed
17.6 | Privacy/security checks cho video/log/artifacts | Testing | QA | P1 – High | 2027-09-23 | 2027-11-02 | Not Started | 0% | 16.8 |  | Privacy/security checklist | Proposed
17.7 | Accessibility/usability checks | Testing | QA | P1 – High | 2027-10-03 | 2027-11-12 | Not Started | 0% | 15.7,16.8 |  | Usability/accessibility test notes | Proposed
18.1 | Xây benchmark harness thống nhất cho accuracy/latency/resource | Research | Research | P0 – Critical | 2027-04-01 | 2027-06-21 | Not Started | 0% | 3.4,7.6 |  | Benchmark harness | Proposed
18.2 | Đo FPS và model latency p50/p95 | AI | AI | P0 – Critical | 2027-04-19 | 2027-07-09 | Not Started | 0% | 18.1,9.8 |  | Runtime latency report | RQ5
18.3 | Đo end-to-end latency và resource profile | Research | Testing | P0 – Critical | 2027-05-08 | 2027-07-28 | Not Started | 0% | 18.1,16.8 |  | E2E performance report | RQ5
18.4 | Chạy robustness: lighting/view/distance/speed/handedness | Research | Research | P0 – Critical | 2027-05-27 | 2027-08-16 | Not Started | 0% | 18.1,5.5,9.8 |  | Robustness report | RQ4
18.5 | Đánh giá NO-SIGN/UNKNOWN false accept / false reject | Research | Research | P0 – Critical | 2027-06-15 | 2027-09-04 | Not Started | 0% | 10.4,16.8 |  | Reliability report | E7
18.6 | Tune confidence threshold trên validation, không dùng final test | AI | AI | P1 – High | 2027-07-04 | 2027-09-23 | Not Started | 0% | 18.5 |  | Threshold configuration | Tránh test leakage
18.7 | Chạy final holdout evaluation một lần sau khi freeze | Research | Research | P0 – Critical | 2027-07-23 | 2027-10-12 | Not Started | 0% | 18.2,18.3,18.4,18.5,18.6 |  | Final evaluation results | Không tune trên final test
18.8 | Tổng hợp error analysis và limitations | Documentation | Documentation | P0 – Critical | 2027-08-11 | 2027-10-31 | Not Started | 0% | 18.7 |  | Final error analysis | Phải ghi cả failure cases
19.1 | Containerize application + AI services | Deployment | Deployment | P1 – High | 2027-11-01 | 2027-11-25 | Not Started | 0% | 16.8 |  | Dockerized prototype | Docker Compose candidate
19.2 | Chuẩn hóa environment/config/secrets | Deployment | Deployment | P1 – High | 2027-11-07 | 2027-12-01 | Not Started | 0% | 19.1 |  | Environment config | Proposed
19.3 | Đóng gói model artifacts + version mapping | AI | AI | P1 – High | 2027-11-14 | 2027-12-08 | Not Started | 0% | 19.1,9.8 |  | Release model package | Proposed
19.4 | Deploy staging/demo environment | Deployment | Deployment | P0 – Critical | 2027-11-21 | 2027-12-15 | Not Started | 0% | 19.1,19.2,19.3 |  | Demo deployment | Proposed
19.5 | Viết Deployment Guide / runbook | Documentation | Documentation | P1 – High | 2027-11-27 | 2027-12-21 | Not Started | 0% | 19.4 |  | Deployment Guide | Proposed
19.6 | Chuẩn bị backup demo/video và offline fallback | Documentation | Documentation | P1 – High | 2027-12-04 | 2027-12-28 | Not Started | 0% | 19.4 |  | Demo backup package | Proposed
20.1 | Chốt paper outline và contribution claims | Research | Research | P1 – High | 2027-06-01 | 2027-08-12 | Not Started | 0% | 9.7,18.1 |  | Paper outline | Claims phải bám evidence
20.2 | Viết Methodology: data, Model A/B/C, transfer protocol | Research | Research | P0 – Critical | 2027-06-17 | 2027-08-28 | Not Started | 0% | 20.1,9.8 |  | Methods draft | Proposed
20.3 | Viết Dataset/Evaluation protocol section | Dataset | Dataset | P1 – High | 2027-07-04 | 2027-09-14 | Not Started | 0% | 20.1,6.7,18.1 |  | Data & evaluation draft | Proposed
20.4 | Viết Experiments: E2–E8 và implementation details | Research | Research | P0 – Critical | 2027-07-21 | 2027-10-01 | Not Started | 0% | 20.2,20.3,18.7 |  | Experiments draft | Proposed
20.5 | Viết Results + error analysis + learning curves | Research | Research | P0 – Critical | 2027-08-07 | 2027-10-18 | Not Started | 0% | 20.4,18.7,18.8 |  | Results draft | Proposed
20.6 | Viết Discussion, limitations, ethics/accessibility | Documentation | Documentation | P1 – High | 2027-08-24 | 2027-11-04 | Not Started | 0% | 20.5 |  | Discussion draft | Không phóng đại
20.7 | Hoàn thiện Related Work từ Literature Matrix | Research | Research | P1 – High | 2027-09-10 | 2027-11-21 | Not Started | 0% | 2.6,20.5 |  | Related Work final | Proposed
20.8 | Tạo full paper draft và internal review | Documentation | Documentation | P0 – Critical | 2027-09-27 | 2027-12-08 | Not Started | 0% | 20.2,20.3,20.4,20.5,20.6,20.7 |  | Research paper draft | Proposed
21.1 | Chốt cấu trúc Final Report theo yêu cầu trường/đề tài | Documentation | Documentation | P1 – High | 2028-01-01 | 2028-01-18 | Not Started | 0% | 20.8 |  | Final report outline | TBD theo form chính thức
21.2 | Cập nhật architecture diagrams / WBS / experiment tables | Documentation | Documentation | P1 – High | 2028-01-05 | 2028-01-22 | Not Started | 0% | 18.8,19.5 |  | Final figures/tables | Proposed
21.3 | Lập traceability Objective → Experiment → Result → Conclusion | Research | Research | P0 – Critical | 2028-01-09 | 2028-01-26 | Not Started | 0% | 18.7,20.8 |  | Traceability matrix | Proposed
21.4 | Hoàn thiện Final Report | Documentation | Documentation | P0 – Critical | 2028-01-13 | 2028-01-30 | Not Started | 0% | 21.1,21.2,21.3 |  | Final Report | Proposed
21.5 | Chuẩn bị slide bảo vệ | Documentation | Documentation | P1 – High | 2028-01-17 | 2028-02-03 | Not Started | 0% | 21.4 |  | Presentation deck | Proposed
21.6 | Chuẩn bị demo script + contingency plan | Final Deliverables | Project Lead | P1 – High | 2028-01-21 | 2028-02-07 | Not Started | 0% | 19.6,21.5 |  | Demo script | Proposed
21.7 | Rehearsal / Q&A / fix cuối | Final Deliverables | Cả nhóm | P0 – Critical | 2028-01-25 | 2028-02-11 | Not Started | 0% | 21.5,21.6 |  | Defense readiness checklist | Proposed
21.8 | Archive source/model/data docs và final deliverables | Documentation | Documentation | P1 – High | 2028-01-29 | 2028-02-15 | Not Started | 0% | 21.4,21.7 |  | Final archive package | Proposed

## 04_PROGRESS_DASHBOARD
VSIGN — PROGRESS DASHBOARD
Dashboard tự động lấy dữ liệu từ Master Gantt / Task Tracker. Timeline baseline: 09/2026–02/2028 (Proposed).
OVERALL PROJECT COMPLETION |  |  | TOTAL TASKS |  | COMPLETED |  |  | DELAYED | BLOCKED
2.878% |  |  | 139 |  | 4 |  |  | 0 | 0
Workstream | Completion | Tasks | Delayed | [6 empty] | Workstream | Completion %
Research | 2.941% | 34 | 0 | [6 empty] | Research | 2.9412
Dataset | 0% | 19 | 0 | [6 empty] | Dataset | 0
AI | 0% | 25 | 0 | [6 empty] | AI | 0
NLP | 0% | 12 | 0 | [6 empty] | NLP | 0
Backend | 0% | 11 | 0 | [6 empty] | Backend | 0
Frontend | 0% | 7 | 0 | [6 empty] | Frontend | 0
Testing | 0% | 7 | 0 | [6 empty] | Testing | 0
Documentation | 6.667% | 15 | 0 | [6 empty] | Documentation | 6.6667
Status | Task Count |  |  | UPCOMING MILESTONES (NEXT 30 DAYS)
Not Started | 129 |  |  | Count | 0
In Progress | 6 |  |  | Overdue Tasks | 0
Review | 0
Blocked | 0 |  |  | Milestone | Target | Status | Phase | Owner
Delayed | 0 |  |  | Project direction baseline locked | 2026-09-30 | Completed | 1 — Project Definition & Research Direction | Project Lead
Completed | 4 |  |  | Literature review & research gap completed | 2026-10-31 | Not Started | 2 — Literature Review | Research
Cancelled | 0 |  |  | Research design / proposal approved | 2026-11-15 | Not Started | 3 — Research Design | Research
|  |  |  | Dataset protocol completed | 2026-11-30 | Not Started | 4 — VSL Dataset Planning | Dataset
|  |  |  | Dataset v1 + signer split ready | 2027-03-31 | Not Started | 6 — Data Processing & Annotation | Dataset
|  |  |  | Model A/B baselines completed | 2027-05-15 | Not Started | 8 — Signer-independent Recognition | AI
|  |  |  | Core TL/data-efficiency/generalization experiments completed | 2027-07-31 | Not Started | 9 — Model Improvement & Experimentation | AI
|  |  |  | Short-sequence + language target reached | 2027-10-15 | Not Started | 11 — Gloss-to-Vietnamese NLP | AI / NLP
|  |  |  | Integrated VSign MVP completed | 2027-11-15 | Not Started | 16 — AI–Software Integration | Project Lead
|  |  |  | Final evaluation completed | 2027-12-31 | Not Started | 18 — Performance & Robustness Evaluation | Research
|  |  |  | Research paper draft completed | 2028-01-31 | Not Started | 20 — Research Paper | Research
|  |  |  | Final project completed | 2028-02-29 | Not Started | 21 — Final Report & Presentation | Project Lead

## 05_RISK_ISSUE
VSIGN — RISK & ISSUE REGISTER
Risk register cấp dự án. Probability/Impact là baseline ban đầu và phải được cập nhật khi có evidence mới.
Risk ID | Risk / Issue | Type | Probability | Impact | Risk Score | Mitigation | Owner | Status
R01 | Không truy cập được VSL400 hoặc external dataset đúng kế hoạch | Risk | Medium | High | 6 | Chuẩn bị source thay thế; self-collected subset; không để project phụ thuộc một nguồn duy nhất. | Dataset | Monitoring
R02 | Thiếu signer diversity trong dữ liệu tự thu | Risk | High | High | 9 | Ưu tiên nhiều signer; giảm repetition nếu cần; ghi limitation rõ. | Dataset | Open
R03 | Data imbalance / label noise | Risk | Medium | High | 6 | QC, class statistics, review label, sampling/loss strategy khi cần. | Dataset | Open
R04 | Signer/session leakage giữa train và test | Risk | Medium | High | 6 | Signer-aware split, dedup, automated leakage audit. | Dataset | Monitoring
R05 | Model overfit và poor unseen-signer generalization | Risk | High | High | 9 | Signer-independent validation/test, transfer learning, regularization, error analysis. | AI | Open
R06 | Scratch vs pretrained experiment không comparable | Risk | Medium | High | 6 | Giữ same architecture/input/split/training budget; predefine protocol. | Research | Monitoring
R07 | Latency cao khiến model nghiên cứu không phù hợp realtime | Risk | Medium | High | 6 | Profile sớm; tách research model và runtime candidate; ONNX/compression nếu cần. | AI | Open
R08 | NO-SIGN/UNKNOWN false acceptance cao | Risk | Medium | High | 6 | Confidence threshold, blank/no-sign class/state, temporal stability, validation-only tuning. | AI | Open
R09 | NLP / language layer làm semantic drift hoặc che lỗi recognition | Risk | Medium | High | 6 | Giữ raw gloss; constrained generation; E8 error propagation; human review. | NLP | Open
R10 | Integration delay giữa AI, backend và frontend | Risk | Medium | Medium | 4 | Chốt model contract/API sớm; integration tests; versioning. | Backend | Open
R11 | Scope creep: full CSLR/mobile/gloss-free quá sớm | Risk | High | High | 9 | MVP-first; Gate cho continuous; stretch/future scope tách riêng. | Project Lead | Monitoring
R12 | Privacy / consent / data retention chưa đầy đủ | Risk | Medium | High | 6 | Hoàn thiện consent, retention, access-control policy trước collection/evaluation chính thức. | Project Lead | Open

## 06_TEAM
VSIGN — TEAM & ROLE DIRECTORY
Tên thành viên ngoài Project Manager hiện để TBD. Có thể thay thế bằng tên thật khi team phân công chính thức.
Member | Role | Workstream | Responsibilities | Contact
Đặng Đại Đạt | Project Manager / Project Lead | Project Management | Scope, priorities, change control, milestones, stakeholder communication
TBD | Research Lead / Researcher | Research | Literature, research gap, RQ, experimental design, analysis, publication
TBD | Dataset Lead | Dataset | Vocabulary, access/license/consent, collection/import, QC, metadata, signer split
TBD | AI Engineer / Researcher | AI | Landmark/video models, transfer learning, training, inference, experiment tracking
TBD | NLP / Language | NLP | Gloss-to-Vietnamese, translation/TTS integration, semantic evaluation
TBD | Backend Developer | Backend | Session/API/database/logging/integration
TBD | Frontend Developer | Frontend | Camera UI, result display, confidence/unknown, accessibility
TBD | QA / Tester | Testing | Data/model/API/E2E/performance/robustness testing
TBD | Documentation | Documentation | Document control, reports, figures/tables, final deliverables
TBD | Deployment | Deployment | Container, environment, staging/demo, runbook

## 07_CONFIG
VSign Project Configuration & Current Direction Baseline
Priority | Status | Owner | Workstream | Risk Level | Risk Status
P0 – Critical | Backlog | Cả nhóm | Project Management | Low | Open
P1 – High | Not Started | Project Lead | Research | Medium | Monitoring
P2 – Medium | In Progress | Research | Dataset | High | Mitigating
P3 – Low | Review | Dataset | AI |  | Accepted
| Blocked | AI | NLP |  | Closed
| Delayed | NLP | Backend
| Completed | Backend | Frontend
| Cancelled | Frontend | Integration
|  | QA | Testing
|  | Documentation | Deployment
|  | Deployment | Research Publication
Final Deliverables
Documentation
CURRENT FINALIZED PROJECT DIRECTION — BASELINE 21/09/2026
Official title (VI) | VSign – Nghiên cứu và phát triển hệ thống nhận diện Ngôn ngữ ký hiệu Việt Nam theo thời gian thực, hiệu quả dữ liệu và có khả năng tổng quát hóa người ký sử dụng học chuyển giao, phục vụ giao tiếp đa ngôn ngữ
Official title (EN) | VSign: A Data-Efficient and Signer-Generalizable Real-Time Vietnamese Sign Language Recognition System Using Transfer Learning for Multilingual Communication
Core research story | Low-resource VSL → Transfer Learning → Data Efficiency → Signer-independent Generalization → Robust Real-Time Recognition → Reliable Multilingual Communication
MVP scope | Proposed 30–50 VSL gloss; multiple signers; signer-independent evaluation; real-time camera; NO-SIGN/UNKNOWN; Vietnamese; ≥1 target language; TTS integration.
Research benchmark | Can expand to 100–400 classes depending data access, compute and experimental feasibility.
Target after MVP | Short sequences 2–5 gloss with temporal smoothing, blank/no-sign and duplicate suppression.
Core models | Model A: hand landmarks + temporal baseline; Model B: hand+pose+selected face; Model C: same RGB/video architecture compared Random-init vs Pretrained-init.
Core experiments | E1 temporal baseline; E2 representation ablation; E3 scratch vs pretrained; E4 10/25/50/75/100% data; E5 seen vs unseen signer; E6 robustness; E7 no-sign/confidence; E8 error propagation.
Current external dataset reference | VSL400 (2026): 74,259 labeled clips, 400 isolated glosses, 28 signers, 3 synchronized RGB views; controlled access. Use subject to Data Usage Agreement.
Translation/TTS position | Application/integration layer behind core VSL recognition; do not train from scratch unless a separate research question is approved.